## 90 Day Plan
Day Range | Week | Workstream | Task | Deliverable | Priority | Owner | KPI | Target Outcome | Dependency | Risk | Status
Days 1-7 | Week 1 | Strategy | Freeze page-level keyword ownership to stop cannibalization | Final keyword-to-URL map approved | P1 | Founder + SEO | Keyword ownership conflicts | 0 conflicts for core pages | Stakeholder alignment | Scope creep | Planned
Days 1-7 | Week 1 | Technical SEO | Validate GSC, GA4, Bing, sitemap, robots, canonicals | Tracking and indexing baseline report | P1 | SEO + Dev | Indexability health | All key pages crawlable/indexable | Access to tools | Misconfigured tracking | Planned
Days 1-7 | Week 1 | Conversion | Define lead qualification fields and CRM flow | New contact form field spec | P1 | Founder + Dev | Lead quality | Form captures budget/timeline/service | CRM mapping | Low lead quality persists | Planned
Days 8-14 | Week 2 | Content Architecture | Refine existing service pages for single primary keyword | Updated 5 core service pages | P1 | SEO + Content | On-page relevance | Clear H1/title/meta per page | Content resources | Mixed page intent | Planned
Days 8-14 | Week 2 | Schema | Audit and patch Service/FAQ/LocalBusiness schemas | Schema validation report | P1 | Dev + SEO | Rich result eligibility | No critical schema errors | Developer bandwidth | Invalid structured data | Planned
Days 8-14 | Week 2 | CRO | Insert CTA blocks every 2 sections on money pages | CTA placement update | P1 | Content + Dev | CTR to contact | +20% click-through to contact page | Design constraints | Weak CTA copy | Planned
Days 15-21 | Week 3 | New Pages | Create MVP development service page | /mvp-development-for-startups-india live | P1 | Content + Dev | BOFU keyword coverage | Page indexed and internally linked | Content draft | Thin content | Planned
Days 15-21 | Week 3 | New Pages | Create custom SaaS development services page | /custom-saas-development-services-india live | P1 | Content + Dev | BOFU keyword coverage | Page indexed and internally linked | Content draft | Cannibalization with existing SaaS page | Planned
Days 15-21 | Week 3 | Internal Linking | Implement fixed blog→service→contact linking rules | Internal link matrix v1 | P1 | SEO + Content | Link depth | All priority pages <=3 clicks from home | Content edits | Orphan pages | Planned
Days 22-30 | Week 4 | Commercial Content | Upgrade pricing page with package bands and qualification cues | Pricing page v2 | P1 | Content + Founder | Commercial conversion | Higher qualified inquiry ratio | Pricing policy clarity | Price mismatch expectation | Planned
Days 22-30 | Week 4 | Proof Assets | Create case study template with measurable outcomes | Case study framework | P1 | Founder + Content | Trust signals | Template approved and reusable | Data availability | No measurable proof | Planned
Days 22-30 | Week 4 | Reporting | Set baseline dashboard for traffic, leads, SQLs, close rate | Weekly SEO dashboard | P1 | SEO | Decision visibility | Single source of truth dashboard | Analytics setup | No reliable baseline | Planned
Days 31-37 | Week 5 | Local SEO | Launch Delhi website development page | /website-development-company-delhi live | P1 | Content + Dev | Local BOFU footprint | Indexed + linked from hub pages | Content approval | Duplicate city content | Planned
Days 31-37 | Week 5 | Local SEO | Launch Delhi app development page | /app-development-company-delhi live | P1 | Content + Dev | Local BOFU footprint | Indexed + linked from hub pages | Content approval | Duplicate city content | Planned
Days 31-37 | Week 5 | CRO | Add sticky consultation CTA on mobile for money pages | Mobile CTA release | P2 | Dev | Mobile conversion rate | +15% mobile contact clicks | UI compatibility | UX friction | Planned
Days 38-44 | Week 6 | Local SEO | Launch Android developer Delhi page | /android-app-developer-delhi live | P2 | Content + Dev | Long-tail local coverage | Indexed + linked | Content resources | Keyword overlap | Planned
Days 38-44 | Week 6 | Trust | Publish first measurable case study | Case study #1 live | P1 | Founder + Content | BOFU conversion assist | Case study linked from 4 service pages | Client permission | Weak proof quality | Planned
Days 38-44 | Week 6 | Trust | Publish second measurable case study | Case study #2 live | P1 | Founder + Content | BOFU conversion assist | Case study linked from 4 service pages | Client permission | Weak proof quality | Planned
Days 45-51 | Week 7 | Content Cluster | Publish SaaS BOFU blog: MVP timeline and budget | 1 SaaS BOFU blog live | P1 | Content | Topical authority | Blog links to 2 service pages + contact | Editorial capacity | Low differentiation | Planned
Days 45-51 | Week 7 | Content Cluster | Publish App BOFU blog: startup app scope and cost | 1 App BOFU blog live | P1 | Content | Topical authority | Blog links to app page + contact | Editorial capacity | Low differentiation | Planned
Days 45-51 | Week 7 | Technical | Run crawl to detect orphan/duplicate/meta conflicts | Crawl issue log + fixes | P1 | SEO + Dev | Technical health | No critical crawl/index issues | Crawl tool access | Hidden duplicate pages | Planned
Days 52-58 | Week 8 | Authority | Start outreach for quality backlinks (founder POV + SaaS topics) | Outreach list + 1st campaign | P1 | Founder + SEO | Referring domains | +5 quality referring domains | Outreach assets | Low acceptance rate | Planned
Days 52-58 | Week 8 | Entity SEO | Add semantic sections to service pages (AI search friendly) | Semantic module updates | P2 | Content + SEO | Answer-engine readiness | Improved query breadth | Content bandwidth | Over-optimization | Planned
Days 52-58 | Week 8 | Schema | Add case-study and article schema where relevant | Schema patch v2 | P2 | Dev + SEO | Structured data coverage | 0 critical schema warnings | Dev bandwidth | Invalid markup | Planned
Days 59-65 | Week 9 | Industry Pages | Launch Fintech industry page | /industries/fintech live | P2 | Content + Dev | Vertical authority | Indexed + linked from services | Content approval | Thin ICP alignment | Planned
Days 59-65 | Week 9 | Industry Pages | Launch Healthcare industry page | /industries/healthcare live | P2 | Content + Dev | Vertical authority | Indexed + linked from services | Content approval | Thin ICP alignment | Planned
Days 59-65 | Week 9 | Lead Quality | Review form submissions and tune qualifiers | Form v2 with qualification logic | P1 | Founder + Dev | SQL rate | Higher lead-to-SQL % | Sufficient data volume | Too strict form | Planned
Days 66-72 | Week 10 | Industry Pages | Launch Retail/D2C industry page | /industries/retail-d2c live | P3 | Content + Dev | Vertical authority | Indexed + linked from services | Content approval | Weak use-case proof | Planned
Days 66-72 | Week 10 | Internal Linking | Deploy v2 links from all ranking blogs to BOFU pages | Internal links matrix v2 | P1 | SEO + Content | BOFU assisted traffic | +25% service-page entries from blog | Content edits | Broken links | Planned
Days 66-72 | Week 10 | CRO | Add consultation hooks on top 5 traffic pages | Conversion module rollout | P1 | Content + Dev | Lead conversion | Higher contact clicks from top pages | Design approval | CTA blindness | Planned
Days 73-79 | Week 11 | Authority | Second backlink campaign (guest posts/digital PR) | Campaign #2 report | P1 | Founder + SEO | Referring domains | +5 additional quality domains | Outreach bandwidth | Low editorial acceptance | Planned
Days 73-79 | Week 11 | Performance | Core Web Vitals improvements on top pages | CWV patch release | P2 | Dev | LCP/INP/CLS | Improved mobile CWV pass rate | Dev cycles | Regression risk | Planned
Days 73-79 | Week 11 | SERP CTR | Rewrite underperforming titles/meta on top impression pages | Meta optimization batch | P2 | SEO + Content | Organic CTR | +15% CTR on target pages | GSC data | Brand voice mismatch | Planned
Days 80-86 | Week 12 | Pruning | Merge/prune weak overlapping blog posts | Content pruning log | P2 | SEO + Content | Cannibalization reduction | Fewer overlapping URLs per keyword | Content decision | Traffic dip on pruned pages | Planned
Days 80-86 | Week 12 | BOFU Expansion | Create 1 comparison page (agency vs freelancer) | Comparison page live | P2 | Content | Commercial assist | Improved BOFU engagement | Research data | Low credibility if generic | Planned
Days 80-86 | Week 12 | Sales Alignment | Map SEO leads to service lines and close rates | SEO-to-revenue mapping | P1 | Founder + Sales | Revenue visibility | Attributed pipeline by page | CRM hygiene | Attribution noise | Planned
Days 87-90 | Week 13 | Review | 90-day SEO audit and re-prioritization | Q2 roadmap doc | P1 | Founder + SEO | Execution quality | Next 90-day roadmap approved | All prior reports | No clear next focus | Planned
Days 87-90 | Week 13 | Forecast | Model traffic/lead/revenue forecast from current trend | Forecast sheet | P1 | Founder | Target realism | Updated lead and revenue targets | Reliable data | Unrealistic assumptions | Planned
Days 87-90 | Week 13 | Decision | Choose expansion direction: city scale vs SaaS authority depth | Strategic decision note | P1 | Founder | Strategic clarity | One clear growth thesis for next quarter | Stakeholder buy-in | Split focus | Planned